## 01_START_HERE
Project Health Command Center
Free Project Health & Risk Diagnostic · by edgeVelocity Labs
Is your project really on track?
Rate 10 health dimensions Green / Amber / Red and get an instant, weighted Project Health Score (0–100), a RAG status, your top 3 attention areas and a one-screen dashboard. No macros, no add-ons.
Before you start: make your own copy (Google Sheets: File › Make a copy · Excel: File › Save As).
Get your health score in 4 steps
1 | Enter your project basics |  | Name, dates, budget, actual spend, % complete and status. Every other tab reads from here.
2 | Rate the 10 dimensions |  | Pick Green, Amber or Red for each dimension and add a comment and next action. The score calculates instantly.
3 | Log risks, milestones and phases |  | Add up to 10 RAID items and 10 milestones, then enter a start and end week for each phase on 08_GANTT.
4 | Review your dashboard |  | Health score, RAG status, top 3 attention areas and live charts. Record the score each week on 07_WEEKLY_SNAPSHOT.
How the score works
Each rating converts to points (Green 90 · Amber 65 · Red 25). The Overall Project Health Score is the weighted average of the dimensions you have rated, so a half-finished check is never penalised. Change a weight on 03_HEALTH_CHECK to reflect what matters most on your project.
90–100 |  | Excellent |  | Keep going. Re-check every 2 weeks.
75–89 |  | Healthy |  | Minor watch items. Review at your next status meeting.
60–74 |  | Attention Required |  | Act this week on your top 3 attention areas.
40–59 |  | At Risk |  | Escalate to your sponsor with a recovery plan.
0–39 |  | Critical |  | Stop and re-baseline scope, schedule and budget.
What's in this workbook
01_START_HERE |  |  | This guide
02_PROJECT_INPUT |  |  | Project basics that feed every other tab, plus budget and time-elapsed checks
03_HEALTH_CHECK |  |  | 10 weighted dimensions, overall score, RAG status and top 3 attention areas
04_RAID_LITE |  |  | Risks, assumptions, issues and dependencies with auto IDs and severity scoring
05_MILESTONES |  |  | Key dates with forecast variance and automatic overdue flags
06_DASHBOARD |  |  | One-screen executive view with 5 live charts
07_WEEKLY_SNAPSHOT |  |  | 4-week health trend with a live 'this week' row to copy from
08_GANTT |  |  | 52-week phase timeline that draws itself, with a current-week marker
Colour key
Your input |  | Cream cells are yours to type in or pick from a dropdown.
Auto-calculated |  | Grey cells hold formulas. Leave them as they are.
Ready for the complete system?
The Advanced Project Planner adds tasks, Kanban, a full Gantt, budget planned vs actual, a complete RAID log, a client view and one-click project reports, all in one Google Sheets workspace.
Explore the Advanced Project Planner ›
Managing capital projects? CapGate Pro splits every hour and invoice into CapEx and OpEx, with audit checks built in.
See CapGate Pro ›
Designed by edgeVelocity Labs · edgevelocity.net

## 02_PROJECT_INPUT
Project Input
Enter your project basics once. Every other tab reads from here.
Your input | Auto-calculated
Field | Your entry | Tip
Project Name | Sample Project Alpha | Shown on the dashboard
Client / Business Unit | Acme Corp
Project Manager | Alex Rivera
Project Sponsor | Priya Shah
Project Start Date | 2026-07-01 | Also sets week 1 on 08_GANTT
Target End Date | 2026-12-31 | Must be after the start date
Current Phase | Execution | Pick from the list
Overall Status (your view) | Amber | Your judgement; compare with the calculated RAG
Planned Budget | 250000 | Whole project, any currency
Actual Spend to Date | 168000
% Complete | 55% | Work done, not time elapsed
Schedule Status | At Risk | Pick from the list
Quick checks (auto-calculated)
Budget Remaining | 82000 | Negative means you are over budget
Budget Used | 67.2% | Compare with % Complete
Time Elapsed | 49.73% | Share of the schedule already used
Days to Target End | 92 | Negative means the target date has passed
Progress vs Time | Ahead of time | % Complete compared with Time Elapsed
Designed by edgeVelocity Labs · edgevelocity.net

## 03_HEALTH_CHECK
Project Health Check
Rate each dimension Green / Amber / Red. Scores, RAG status and attention areas calculate automatically.
[6 empty] | Your input | Auto-calculated
# | Dimension | Rating | Weight | Points | Weighted | Comment / Observation | Recommended Action
1 | Scope | Amber | 1 | 65 | 65 | Some scope creep from change requests. | Re-baseline scope with sponsor sign-off. | 64.9901 | 5
2 | Schedule | Red | 1.5 | 25 | 37.5 | Two sprints behind original plan. | Add resources or replan the critical path. | 24.9851 | 1
3 | Budget | Amber | 1.5 | 65 | 97.5 | 12% over plan to date; trending tighter. | Tighten the forecast and review remaining spend. | 64.9851 | 2
4 | Resources | Green | 1 | 90 | 90 | Team fully staffed, no major gaps. | No action needed. | 89.9901 | 7
5 | Quality | Green | 1 | 90 | 90 | QA passing, no major defects open. | Continue the current QA cadence. | 89.9901 | 8
6 | Risks | Amber | 1.5 | 65 | 97.5 | Vendor delivery risk being monitored. | Escalate the vendor risk and confirm the delivery date. | 64.9851 | 3
7 | Dependencies | Green | 1 | 90 | 90 | One legal dependency outstanding. | Follow up with legal for sign-off this week. | 89.9901 | 9
8 | Stakeholders | Green | 0.75 | 90 | 67.5 | Sponsor engaged, steering committee aligned. | No action needed. | 89.9927 | 10
9 | Communication | Amber | 0.75 | 65 | 48.75 | Status reporting cadence occasionally slips. | Set a fixed weekly reporting slot. | 64.9927 | 6
10 | Delivery Readiness | Amber | 1.5 | 65 | 97.5 | On track overall but watch budget and schedule. | Monitor budget and schedule closely. | 64.9852 | 4
Summary | [5 empty] | Top 3 Attention Areas (lowest points first, heaviest weight breaks ties)
Overall Health Score |  |  | 68 |  |  | Dimension | Recommended Action
Health Label |  |  | Attention Required |  |  | 1. Schedule (Red) | Add resources or replan the critical path.
RAG Status |  |  | Amber |  |  | 2. Budget (Amber) | Tighten the forecast and review remaining spend.
Dimensions Rated |  |  | 10 of 10 |  |  | 3. Risks (Amber) | Escalate the vendor risk and confirm the delivery date.
Green |  |  | 4 |  |  | Green dimensions are never listed. Clear an attention area by fixing it, then re-rate it.
Amber |  |  | 5
Red |  |  | 1
Designed by edgeVelocity Labs · edgevelocity.net

## 04_RAID_LITE
RAID Lite
A compact Risks · Assumptions · Issues · Dependencies log for up to 10 items. IDs and severity calculate automatically.
[10 empty] | Your input | Auto-calculated
ID | Type | Title | Description | Owner | Probability | Impact | Score | Severity | Status | Next Review | Mitigation / Action
R1 | Risk | Key vendor delivery delay | Vendor may miss the agreed hardware delivery window. | Alex | Medium | High | 6 | High | Monitoring | 2026-10-02 | Weekly check-in with the vendor account manager.
I1 | Issue | Budget overspend | Actual spend is 12% over plan to date. | Priya |  | High | 9 | High | Open | 2026-10-06 | Review scope and remaining spend with finance.
D1 | Dependency | Legal sign-off on contract | Vendor onboarding cannot start until the MSA is signed. | Jordan | Low | High | 3 | Medium | Escalated | 2026-10-01 | Escalated to the legal lead for priority review.
A1 | Assumption | Test environment ready by UAT | Infrastructure team confirms the UAT environment by week 10. | Alex | Medium | Medium | 4 | Medium | Open | 2026-10-09 | Confirm the environment date in the next infra sync.
Score = Probability × Impact (Low 1 · Medium 2 · High 3). Issues have already happened, so they score as High probability. Overdue review dates turn red.
Summary |  |  |  |  | Items by Type
Total RAID Items |  |  | 4
Open Items |  |  | 4
High Severity (open) |  |  | 2
Reviews Overdue |  |  | 0
Risks |  |  | 1
Assumptions |  |  | 1
Issues |  |  | 1
Dependencies |  |  | 1
Designed by edgeVelocity Labs · edgevelocity.net

## 05_MILESTONES
Milestones
Track up to 10 key dates. Variance and overdue flags calculate automatically.
[7 empty] | Your input | Auto-calculated
Milestone | Owner | Planned Date | Actual / Forecast | Variance (days) | Status | % Complete | Flag | Notes
Requirements Sign-off | Priya | 2026-08-02 | 2026-08-04 | 2 | Complete | 100% | Done | Signed off two days late.
Design Review | Alex | 2026-08-22 | 2026-08-22 | 0 | Complete | 100% | Done | No major findings.
Vendor Hardware Delivery | Alex | 2026-09-16 | 2026-10-02 | 16 | Delayed | 40% | Overdue | Vendor confirmed a two-week slip.
UAT Complete | Jordan | 2026-10-06 | 2026-10-13 | 7 | At Risk | 10% | Due soon | Depends on the hardware delivery.
Go-Live | Priya | 2026-10-26 |  |  | Not Started | 0%
Variance = forecast minus planned date (positive = late). Flag: Overdue once the planned date has passed and the milestone isn't complete; Due soon within 14 days.
Summary |  |  |  | Milestones by Status
Total Milestones |  | 5
Complete |  | 2
On Track |  | 0
At Risk |  | 1
Delayed |  | 1
Not Started |  | 1
Overdue |  | 1
Designed by edgeVelocity Labs · edgevelocity.net
Formulas:
Flag = IF([Milestone]="","",IF([Status]="Complete","Done",IF(AND([Planned Date]<>"",[Planned Date]<TODAY()),"Overdue",IF(AND([Planned Date]<>"",[Planned Date]-TODAY()<=14),"Due soon",""))))

## 06_DASHBOARD
Project Health Command Center
Project Health Dashboard · Sample Project Alpha
HEALTH SCORE | RAG STATUS |  | % COMPLETE | BUDGET USED | SCHEDULE | OPEN RAID ITEMS
68 | Amber |  | 55% | 67.2% | At Risk | 4
Attention Required | 4 Green · 5 Amber · 1 Red |  | Time elapsed 50% | 168,000 of 250,000 | Target 31 Dec 2026 | 2 high severity · 0 overdue
Health by Dimension
Dimension | Rating | Points
Scope | Amber | 65 |  |  |  |  | Scope | 0 | 65 | 0
Schedule | Red | 25 |  |  |  |  | Schedule | 0 | 0 | 25
Budget | Amber | 65 |  |  |  |  | Budget | 0 | 65 | 0
Resources | Green | 90 |  |  |  |  | Resources | 90 | 0 | 0
Quality | Green | 90 |  |  |  |  | Quality | 90 | 0 | 0
Risks | Amber | 65 |  |  |  |  | Risks | 0 | 65 | 0
Dependencies | Green | 90 |  |  |  |  | Dependencies | 90 | 0 | 0
Stakeholders | Green | 90 |  |  |  |  | Stakeholders | 90 | 0 | 0
Communication | Amber | 65 |  |  |  |  | Communication | 0 | 65 | 0
Delivery Readiness | Amber | 65 |  |  |  |  | Delivery Readiness | 0 | 65 | 0
Top 3 Attention Areas | [6 empty] | Green | 4
1. Schedule (Red) |  |  | Add resources or replan the critical path. |  |  |  | Amber | 5
2. Budget (Amber) |  |  | Tighten the forecast and review remaining spend. |  |  |  | Red | 1
3. Risks (Amber) |  |  | Escalate the vendor risk and confirm the delivery date.
[7 empty] | Complete | 2
RAG Distribution |  |  | Milestones by Status |  | RAID Items by Type |  | On Track | 0
[7 empty] | At Risk | 1
[7 empty] | Delayed | 1
[7 empty] | Not Started | 1
[7 empty] | Risks | 1
[7 empty] | Assumptions | 1
[7 empty] | Issues | 1
[7 empty] | Dependencies | 1
Health Trend (from 07_WEEKLY_SNAPSHOT)
Want the complete system? The Advanced Project Planner adds tasks, Kanban, full Gantt, budget tracking, RAID management and reports.
Explore the Advanced Project Planner ›
Designed by edgeVelocity Labs · edgevelocity.net

## 07_WEEKLY_SNAPSHOT
Weekly Health Snapshot
Record your scores once a week to see the trend. Copy the live row into the next empty week.
[5 empty] | Your input | Auto-calculated
Week | Health Score | Schedule | Budget | Risk | RAG | Note
Week 1 | 78 | 75 | 80 | 70 | Green | Kick-off complete, team onboarded.
Week 2 | 74 | 60 | 72 | 65 | Amber | First sprint slipped by three days.
Week 3 | 70 | 45 | 68 | 65 | Amber | Vendor flagged a possible delay.
Week 4 | 68 | 25 | 65 | 65 | Amber | Two sprints behind; recovery plan in progress.
This week (live) | 68 | 25 | 65 | 65 | Amber | Live from 03_HEALTH_CHECK. Copy into the next week.
Schedule, Budget and Risk are the points for those three dimensions on 03_HEALTH_CHECK (Green 90 · Amber 65 · Red 25).
Trend
Designed by edgeVelocity Labs · edgevelocity.net

## 08_GANTT
High-Level Gantt
Enter a start week and end week for each phase. The bar draws itself; the gold column marks the current week.
Week 1 starts |  | 2026-06-29 |  |  | Now | 14
Month | [5 empty] | Jun | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun
Week starting (Monday) | [5 empty] | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21
# | Phase / Activity | Owner | Start Wk | End Wk | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | Initiation & Planning | Alex | 1 | 3 | 3 | bar: Jun 29 to Jul 13
2 | Requirements & Design | Priya | 2 | 5 | 4 | bar: Jul 6 to Jul 27
3 | Build / Execution | Jordan | 5 | 11 | 7 | bar: Jul 27 to Sep 7
4 | Testing & UAT | Alex | 10 | 14 | 5 | bar: Aug 31 to Sep 28
5 | Go-Live & Closure | Priya | 14 | 16 | 3 | bar: Sep 28 to Oct 12
6
7
8
9
10
11
12
Weeks run Monday to Sunday, starting from the week your project starts. Shaded bands mark alternate months. An end week before the start week turns red. Up to 12 phases across 52 weeks.
Designed by edgeVelocity Labs · edgevelocity.net